Business Case Templates
To support better investment decisions and better procurement

The aim of the business case template family is to support your thinking, writing and engagement with stakeholders and compliance with best practice. These templates provide a framework for scoping and planning spending proposals, to support evidence based decision-making. They avoid a “one-size fits all” approach and should be used proportionately.

The two Single-Stage Business Case templates are based on the Five Case Model and follow the Better Business Cases Guidance. They have been developed by the International Better Business Case Programme.

The Five Case Model can be used for the preparation of:
- Programme Business Cases (PBC),
- Project Business Cases (three stage: SOC, OBC, FBC),
- Business Justification Cases (BJC)
- Policies and Strategies.

It is all about: Thinking, Evidencing, and Documenting. Business cases should be clear, concise, and avoid unnecessary repetition.

Which template should be used?

Consider:
- the value thresholds (see guidance below),
- the complexity and risk involved,
- whether the situation is novel or contentious,
- whether procurement is required and the scale of the procurement, and
- whether there are any dependencies, e.g. with business as usual matters or other projects?
When in doubt, consider using the higher value business case templates, which provide more structure and support. Contact your local office for advice, support and training.

TEMPLATES / For Procurements and Projects (enabling outputs, activities and infrastructure): / Single Stage Business Case - Low Value and Risk (£0 to £250k value of procurement). / Single Stage Business Case - Medium Value and Risk (£250k to £2 million value of procurement) / Three Stage Business Case (SOC, OBC, FBC) – High Value (Over £2 million value of procurement) [1] / For Overarching Programmes (outcomes to be achieved through improved services comprised of enabling projects): / Programme Business Case using the Five Case Model[2]
[1] See Better Business Case Five Case Model Project Guidance: https://gov.wales/guide-developing-project-business-case
[2] See Better Business Case Five Case Model Programme Guidance: https://gov.wales/guide-developing-programme-business-case

Questions or feedback on our templates and guidance?
Contact us at: BetterBusinessCasesMailbox@gov.wales

<Title of Investment Proposal>

FULL BUSINESS CASE (FBC) – HIGH VALUE (OVER £2 MILLION VALUE OF PROCUREMENT)

SRO:
Project Manager:
Organisation:

	Name	Signature	Date
Prepared by:
Reviewed by:
Approved by:

This template is based on the Five Case Model and follows the Better Business Case Guidance. It has been developed by the International Better Business Case Programme.
Full Business Case (FBC) template

This template should be completed in conjunction with the Better Business Cases Guide to developing the Project Business Case. The relevant steps and actions in the Guidance are provided.

The purpose of the FBC is to select the most economically advantageous tender and to put in place the management arrangements for the successful delivery of the project’s outputs and activities.

Heading	Action	Guidance reference
		Step 8 – Procuring the Value for Money (VFM) solution
Strategic Case	Revisit the Case for Change / Confirm that the case for change remains as set out in the Outline Business Case (OBC) and that the spending objectives for the project are specific, measurable, achievable, relevant and time constrained (SMART) for the purposes of post-project evaluation.	Action 25
Economic Case	Revisit the OBC options / Confirm that the options identified in the OBC are still valid and their rankings remain the same.	Action 26
	Detail procurement arrangements and evaluation of best and final offers (BAFO’s). / Provide a summary of the procurement process and prepare economic appraisals for each of the “short listed” service providers at the BAFO stage, which reflect “whole life cost”, suitably risk adjusted.	Action 27
		Step 9 – Contracting for the Deal
Commercial Case	Set out the negotiated Deal and contractual arrangements / Use the standard headings for the Commercial Case to document the negotiated Deal between the public sector and its choice of service provider.	Action 28
Financial Case	Set out the financial implications of the Deal / Use the standard headings for the Financial Case to document the affordability and fundability of the project and attach the financial appraisal for the scheme.	Action 29
Management Case		Step 10 – Ensuring Successful Delivery
	Finalise project management arrangements and plans / Revisit the project management arrangements and plans outlined in the OBC and explain what has been agreed for the successful delivery of the project. / Attach the project plan. Highlight any vacancies within the project delivery team and how it is intended to fill them.	Action 30
	Finalise change arrangements and plans / Revisit the change management arrangements and plans outlined in the OBC and explain what has been agreed for the successful delivery of the project. / Attach the latest version of the change management plan to the FBC.	Action 31
	Finalise benefits realisation arrangements and plans. / Revisit the benefits realisation arrangements and plans outlined in the OBC and explain what has been agreed for the successful delivery of the project. / Attach the latest version of the benefits register to the FBC.	Action 32
	Finalise risk management arrangements and plans / Revisit the risk management arrangements and plans outlined in the OBC and explain what has been agreed for the successful delivery of the project. / Attach the latest version of the risk register to the FBC. / Include a contingency plan to manage the risk of service failure in the design, build and operational phases.	Action 33
	Finalise contract management arrangements and plans / Record the contract management arrangements and plans that have been agreed between the organisation and the supply side.	Action 34
	Finalise post-project evaluation arrangements and plans / Revisit the project assurance and post-project evaluation arrangements and plans outlined in the OBC and explain what has been agreed for the successful delivery of the project. / Project assurance arrangements should include the use of Cabinet Office Gateways and other sources of assurance. / Post evaluation arrangements should include the use of project implementation reviews (PIR) and post evaluation reviews (PER), including the use of Gateway 5 (Benefits Realisation).	Action 35
Project Assurance	Undertake a review of the project’s ability to successfully deliver the agreed outputs and activities	Gateway 3 (Investment Decision)