Business Case Templates
To support better investment decisions and better procurement

The aim of the business case template family is to support your thinking, writing and engagement with stakeholders and compliance with best practice. These templates provide a framework for scoping and planning spending proposals, to support evidence based decision-making. They avoid a “one-size fits all” approach and should be used proportionately.

The two Single-Stage Business Case templates are based on the Five Case Model and follow the Better Business Cases Guidance. They have been developed by the International Better Business Case Programme.

The Five Case Model can be used for the preparation of:
- Programme Business Cases (PBC),
- Project Business Cases (three stage: SOC, OBC, FBC),
- Business Justification Cases (BJC)
- Policies and Strategies.

It is all about: Thinking, Evidencing, and Documenting. Business cases should be clear, concise, and avoid unnecessary repetition.

Which template should be used?

Consider:
- the value thresholds (see guidance below),
- the complexity and risk involved,
- whether the situation is novel or contentious,
- whether procurement is required and the scale of the procurement, and
- whether there are any dependencies, e.g. with business as usual matters or other projects?
When in doubt, consider using the higher value business case templates, which provide more structure and support. Contact your local office for advice, support and training.

TEMPLATES / For Procurements and Projects (enabling outputs, activities and infrastructure): / Single Stage Business Case - Low Value and Risk (£0 to £250k value of procurement). / Single Stage Business Case - Medium Value and Risk (£250k to £2 million value of procurement) / Three Stage Business Case (SOC, OBC, FBC) – High Value (Over £2 million value of procurement) [1] / For Overarching Programmes (outcomes to be achieved through improved services comprised of enabling projects): / Programme Business Case using the Five Case Model[2]
[1] See Better Business Case Five Case Model Project Guidance: https://gov.wales/guide-developing-project-business-case
[2] See Better Business Case Five Case Model Programme Guidance: https://gov.wales/guide-developing-programme-business-case

Questions or feedback on our templates and guidance?
Contact us at: BetterBusinessCasesMailbox@gov.wales

<Title of Investment Proposal>

PROGRAMME BUSINESS CASE (PBC) - HIGH VALUE (OVER £2 MILLION VALUE OF PROCUREMENT)

SRO:
Project Manager:
Organisation:

	Name	Signature	Date
Prepared by:
Reviewed by:
Approved by:

This template is based on the Five Case Model and follows the Better Business Case Guidance. It has been developed by the International Better Business Case Programme.
 Programme Business Case (PBC) template

This template should be completed in conjunction with the Better Business Cases Guide to developing the Programme Business Case. The relevant steps and actions in the Guidance are provided.

The purpose of the PBC is to select the projects and activities required to deliver the programme’s spending objectives in support of the agreed strategy for the delivery of policy objectives.

Business Case heading	Action	Guidance reference
Strategic assessment	Determine how the programme aligns with other programmes and projects within the Organisation’s business strategy and strategic portfolio, and supports wider public sector objectives.	Step 1, action 1
Assurance	Undertake a review of the strategy	Gate 0 (strategic assessment)
Executive Summary	4 to 5 pages maximum predicated on the Five Case Model. / In the first paragraph outline the programme and spend for which approval is being sought.
Strategic Case	Undertake a facilitated workshop for the completion of step 2 – making the case for change (workshop 1 refers). Ensure that the Senior Responsible Owner (SRO) attends along with key stakeholders and end users.	Step 2 – Making the Case for Change
Strategic Context / Organisational Overview	Provide a brief overview of the organisation(s) making the case for intervention and change.	Action 2
Business strategy and aims	Explain how the programme supports the existing policies and strategies of the organisation and aligns with other programmes and projects within the strategic portfolio.	Action 2 continued
Other relevant strategies	National, regional and other organisations’ strategies refer. Keep this section to a minimum and attach relevant documents, if applicable.	Action 2 continued
The Case for Change / Spending objectives	Specify the spending objectives for the programme. These should focus on the target outcomes for the intervention and be SMART. / Desired outcomes include: improved economy, efficiency, effectiveness, replacement and compliance.	Action 3
Existing arrangements	Provide a factual picture of the organisation’s current service model. Business as Usual (BAU) refers.	Action 3 continued
Business needs – current and future	Specify the organisation’s business needs in terms of the service improvements required to achieve the agreed spending objectives. Focus on the “service gaps”.	Action 3 continued
Potential scope and service requirements	Identify the potential scope for the programme in terms of the outcomes, service changes and operational capabilities required. / Focus on the projects - outputs and key activities - required to close the “service gaps” identified on a continuum of need: core (essential); desirable and optional.	Action 4
Main benefits	Specify the main benefits associated with the achievement of the programme’s spending objectives by category, beneficiary and class. Distinguish benefits from outcomes.	Action 5
Main risks	Specify the main risks associated with the achievement of the programme’s spending objectives and propose counter measures for avoidance, mitigation and management.	Action 5 continued
Constraints	Specify any constraints that have been placed on the project. These should not be artificially imposed.	Action 5 continued
Dependencies	Specify any dependencies outside the scope of the programme upon which the success of the programme is dependent.	Action 5 continued
Economic Case	Undertake a facilitated workshop for the completion of step 3 (workshop 2 refers). Ensure that the Senior Responsible Owner (SRO) attends with key stakeholders and end users.	Step 3 – Exploring the preferred way forward
Critical success factors (CSFs)	Agree critical success factors. / Generic CSF’s include: strategic fit and business needs; value for money; supply side capacity and capability; affordability and achievability. Tailor accordingly.	Action 6
Long listed Options	Determine the long list options and undertake SWOT (strengths, weaknesses, opportunities, threats) analysis. / Headings must include: description, advantages, disadvantages and conclusions in terms of how well the option meets the agreed spending objectives and CSF’s for the programme. / Use must be made of the Options Framework Filter to disaggregate potential options for the programme, in terms of their potential scope, solution, method of service delivery, implementation and funding. / The evidence base and all sources and assumptions must be recorded.	Action 7
Preferred Way Forward	Identify the preferred way forward for the programme – scope, solution, service delivery, implementation and funding – together with the short list options against which the preferred way forward will be appraised.	Action 8
Shortlisted Options	Describe the programme short list. This should include a minimum of 3 to 4 options, including: / Business as Usual (BAU) / A realistic “do minimum” based on the core requirements for the project / The recommended preferred way forward / One or more possible options based on more or less ambitious combinations of the preferred way forward.	Action 8 continued
NPSC/NPSV findings	Indicative net present social value (NPSV), net present social cost (NPSC) and benefit cost ratios (BCR) should be provided for the short list options. The HM Treasury Green Book summary table should be used for this purpose. / Allowances should be made for optimism bias. / Indicative benefits must be included. / The evidence base and all relevant sources and assumptions must be recorded. / Multi Criteria Decision Analysis (MCDA) using swing weighting and a professionally qualified facilitator must be restricted to options for the scope and means of achievement within the long list.	Action 8 continued
Commercial, Financial and Management Cases	Provide an overview of these Cases in support of the preferred way forward for the Programme.
	An early version of the Programme Business Case (PBC) is now available and should be considered for the approval of the Programme Board
Programme assurance	Undertake a review of the programme.	Gate 0 (strategic assessment)

Business Case heading	Action	Guidance reference
	Consider the use of a facilitated workshop for the completion of step 4 and assessment of the short-listed options (workshop 3 refers).	Step 4 – Determining potential Value for Money (VfM)
Strategic and Economic Cases	Revisit the Programme Business Case (PBC) and confirm the recommended short list.	Action 9
Economic Case / NPSC/NPSV Findings	Prepare the economic appraisals for the short list options / These must be prepared in accordance with the HM Treasury Green Book guidance and summarised in the table provided. The net present social value (NPSV), or net present social cost (NPSC), and the benefit cost ratio (BCR) must be provided for each option. / All assumptions and sources must be recorded.	Action 10
Benefits appraisal	Undertake benefits appraisal. / Benefits should be identified by beneficiary (recipient) and class (type) for the following categories: / Direct public sector benefits (to originating organisation) / Indirect public sector benefits (to other public sector organisations) / Wider benefits to UK society (eg households, individuals, businesses). / The approach to benefits appraisal should be prudent, proportionate and evidence based. All benefits should be recorded in the benefits register.	Action 11
Risk Assessment	Undertake risk appraisal. / As the proposal develops, allowances for optimism bias should be reduced and replaced by measured risk (£). All risks must be recorded in the risk register.	Action 12
Preferred Option / Sensitivity Analysis	Select preferred option and undertake sensitivity analysis. / Complete the summary table outlined in the HM Treasury Green Book. / The preferred option should be a balanced judgement based on the net present social value (NPSV), the Benefit Cost Ratio (BCR) and the level of risk involved; or alternatively, the lowest net present social cost (NPSC). Any unmeasured or unquantified (£) benefits must be explained in full.	Action 13
Commercial Case	Consider the use of a facilitated workshop for step 5 – preparing the Deal (workshop 4 refers).	Step 5 – Preparing for the potential Deal
Procurement Strategy and route	Determine procurement strategy for the programme in accordance with the Commercial Strategy for the Organisation, which should reflect the Cabinet Office’s Crown Commercial Operating Standards. / Explain how the programme’s key outputs and activities will be procured in accordance with relevant procurement rules and regulations. / Reference the Organisation’s Commercial Strategy and commitment to Crown Commercial Operating Standards, as required.	Action 14
Service requirements and outputs	Determine service streams and required outputs. / Identify the programme service streams and projects required, and the potential Deals to be made with public and private sector service providers. / Attach a copy of the advertisement, if applicable.	Action 15
Risk allocation	Outline potential risk apportionment / Identify how the service risks in the design, build, funding and operational phases of the programme may be apportioned between the public and private sectors.	Action 16
Charging mechanism	Outline potential payment mechanisms. / Identify how the programme intends to make payment for its key services and outputs over the expected lifespan of the contract(s) and to tie down risks in the charging mechanism.	Action 17
Key contractual arrangements / Personnel implications / Accountancy treatment	Ascertain contractual issues and accountancy treatment. / Outline the contractual arrangements for the programme, including the use of particular contracts, the key contractual issues for the Deals and its accountancy and personnel implications (if any).	Action 18
Financial Case		Step 6 - Ascertaining affordability and funding requirement
	Prepare financial model and financial appraisals.	Action 19
Capital and revenue requirements	The financial appraisal for the preferred option must be prepared in accordance with the guidance provided in the HM Treasury Green Book. / Whole life costs are required. / Note: the economic and financial appraisals are treated differently.	Action 19 continued
Net effect on prices (if any)	The implications for any prices that the organisation charges for its services must be explained.	Action 19 continued
Impact on balance sheet	The impact on the organisation’s balance sheet must be explained. This includes depreciation, impairment, and any contingent liabilities or capital changes.	Action 19 continued
Impact on income and expenditure account	The impact of the organisation’s income and expenditure account must be explained, if applicable.	Action 19 continued
Overall affordability and funding	A summary of the overall affordability and funding of the programme must be provided, together with an assessment of how any shortfalls in available funding will be covered.	Action 19 continued
Confirmation of stakeholder support	This must be provided where other public sector organisations are funding the programme’s outputs and services.	Action 19 continued
Management Case	Consider a facilitated workshop for the completion of step 7 – planning the arrangements required for the successful delivery of the programme (workshop 5 refers).	Step 7 – Planning for successful delivery
Programme and project management governance arrangements	Plan programme management – strategy, frameworks and plans. / Record the risk profile assessment (RPA) and the Senior Responsible Owner (SRO) for the programme. / Set out the governance arrangements, including key roles and responsibilities. / Provide an outline of the project plan, including key milestones.	Action 20
Use of specialist advisers	Specify what is required by way of external support: legal, technical and business expertise etc.	Action 20 continued
Change and Contract management arrangements	Plan change and contract management – strategy, frameworks and plans. / Explain how change will be managed.	Action 21
Benefits Realisation arrangements	Plan benefits realisation – strategy, framework and plans / Complete the benefits register in accordance with HM Treasury Green Book guidance and attach to the business case. Confirm that the benefits register is an integral part of programme management meetings.	Action 22
Risk management arrangements	Plan risk management – strategy, framework and plans. / Complete the risk register in accordance with HM Treasury Green Book guidance and attach to the business case. Confirm that the benefits register is an integral part of programme management meetings.	Action 23
Programme assurance / Post implementation and evaluation arrangements	Plan programme assurance and post evaluation – strategy, framework and plans. / Set out the arrangements for programme assurance, including the use of Cabinet Office Gateway Reviews. Other sources of assurance should be considered: technical, quality etc. / Specify the probable timescales for undertaking programme implementation and post evaluation reviews, including Cabinet Office Gateway Review 5 (Benefits Realisation).	Action 24
Contingency arrangements and plans	Set out the contingency plans in the event of any delays or disruptions to anticipated services.	Action 24 continued
Programme assurance	Undertake a review of the programme.	Gate 0 (strategic assessment)